AETHERVAULT TRADER

Complete Accelerated Learning and Build Roadmap

From Complete Beginner to Professional C Developer to Fully Working Project

19 June 2026  –  15 July 2026

26 Days  |  4-6 Hours Per Day  |  ~120 Hours Total

Based on: Bro Code C Programming Full Course (7-hour) + Curated Gap-Fillers

IMPORTANT: ACCELERATED SCHEDULE NOTICE The original 8-week roadmap ran 3 Jun – 28 Jul at 2-3 hours/day. This version has been restructured to start 19 June and deliver a FULLY WORKING AetherVault Trader by 15 July — 26 days total. NO content has been removed. ALL gap-fillers, ALL practice tasks, ALL concepts are present. The only change is intensity: you will need 4-6 hours per day instead of 2-3. Rest days are preserved after every 3-day phase block. If you miss a day, add those hours to the next session — the 15 July deadline does not move.

# A.  Project Overview and Why This Roadmap Works

AetherVault Trader is not a toy project — it is a fully-featured, intermediate-to-advanced C application that touches every critical concept of the language. Every single phase of this roadmap exists because AetherVault demands it. You will not learn a concept in isolation; you will learn it because a specific, named feature of the simulator requires it. When malloc feels abstract, remember: it is the only reason users can hold unlimited stocks. When file I/O feels dry, remember: it is the exact mechanism behind your save/load system. This roadmap is honest about difficulty. Pointers, dynamic memory, and structs-with-pointers will challenge you. Follow the strict learning-first rule without exception. Every hour on the fundamentals saves days of confusion during the build phase.

## Core AetherVault Requirements at a Glance

| Module | Key Requirement | Primary C Concept |
| --- | --- | --- |
| Market Engine | 10+ stocks, random walk with drift, price history (50 ticks) | rand(), math.h, arrays, structs |
| Trading System | Buy/sell, 0.5% fee, full input validation | Functions, loops, structs, pointers |
| Portfolio | Dynamic table: symbol, qty, avg price, P&L | Struct arrays, printf formatting, ANSI codes |
| Dynamic Data | Unlimited stocks and transactions — no fixed limits | malloc, calloc, realloc, free |
| Persistence | Binary save/load of entire portfolio + transaction log | fwrite/fread, file I/O with structs |
| Risk Engine | Volatility, Beta, diversification score, ASCII chart | Math formulas, loops, string output |
| Professional UI | Menus, ANSI colours, formatted tables, clear errors | ANSI escapes, printf width/precision |
| Extra Features | Stock search, transaction filter, dashboard | String compare, modular functions |

# B.  Master Calendar — 19 Jun to 15 Jul 2026

4-6 hours per day  |  3-day phase blocks  |  1 rest day after each block  |  Zero skipped content

| Phase | Days | Dates | Hrs | Theme | Milestone Goal |
| --- | --- | --- | --- | --- | --- |
| Phase 1 | Days 1-3 | 19-21 Jun | 12 h | C Foundations, Variables, I/O | Formatted mock stock price table in console |
| Phase 2 | Days 4-6 | 22-24 Jun | 12 h | Control Flow, Loops, Functions | Full console menu with input validation loop |
| Phase 3 | Days 7-9 | 25-27 Jun | 12 h | Arrays, Strings, String Functions | Search hardcoded stock list by symbol using strcmp() |
| Phase 4 (Critical) | Days 10-12 | 28-30 Jun | 15 h | POINTERS — Deep Dive (most critical) | Pass and modify a struct through pointer; draw 5 memory diagrams |
| Phase 5 | Days 13-15 | 1-3 Jul | 12 h | Structs, Typedef, Nested Structs | Define all 4 AetherVault structs; create, modify, print via pointer |
| Phase 6 (Critical) | Days 16-18 | 4-6 Jul | 15 h | Dynamic Memory: malloc, calloc, realloc, free | Dynamic struct array grows with realloc; zero Valgrind leaks |
| Phase 7 | Days 19-21 | 7-9 Jul | 12 h | File I/O, Math, Random Walk, ANSI, time.h | Save/load dynamic struct array; colour-coded terminal table |
| BUILD PHASE | Days 22-26 | 10-15 Jul | 36 h | Full Project Build — All 12 Features | FULLY WORKING AetherVault Trader by 15 Jul |

# C.  Detailed Phase-by-Phase Roadmap

| PHASE 1 — C Foundations: Variables, Operators, I/O | 19 Jun – 21 Jun 12 Hours | 3 sessions × 4 hrs |
| --- | --- | --- |

Bro Code Timestamps to Watch

- 0:00:00 – 0:04:23   Introduction and course overview

- 0:04:24 – 0:08:44   Setup: compiler (GCC), IDE (VS Code + Code::Blocks)

- 0:08:45 – 0:22:09   Variables and data types: int, float, double, char, _Bool

- 0:22:10 – 0:28:29   Format specifiers: %d, %f, %lf, %c, %s, %.2f

- 0:28:30 – 0:32:59   Constants: const keyword and #define macros

- 0:33:00 – 0:42:59   Arithmetic operators, augmented assignment (+=, -=, *=, /=)

- 0:43:00 – 0:54:59   User input with scanf()

- 0:55:00 – 1:01:59   Math.h: sqrt(), pow(), fabs(), ceil(), floor()

Gap Analysis — What Bro Code Does NOT Cover

- printf column alignment: %10s, %-10s, %8.2f — critical for ALL portfolio tables in AetherVault

- #define macros for project constants (TRANSACTION_FEE 0.005, MAX_SYMBOL_LEN 8) — barely touched

- Right-padding and left-padding strings for formatted console tables — completely absent

- The dangerous fflush(stdin) vs. correct getchar() pattern for clearing the input buffer after scanf()

- Using %.6f vs %e for financial precision and when each is appropriate — not discussed

- Operator precedence traps: why (a+b)/2 and a+b/2 produce different results — glossed over

- The difference between integer division and floating-point division: 5/2==2 but 5.0/2==2.5

Gap-Filler Resources

- YouTube: “C printf formatting table columns alignment tutorial”

- YouTube: “C format specifiers complete guide freeCodeCamp”

- YouTube: “C #define constants vs const best practice”

- YouTube: “C scanf input buffer flush getchar fix”

- CS50 Week 1 lecture — first-principles variable explanation, free at cs50.harvard.edu

- YouTube: “C integer vs float division explained”

Project Relevance — AetherVault Trader Connection

- Portfolio table uses: %-8s %6d %10.2f %10.2f %12.2f for symbol/qty/price/value columns

- TRANSACTION_FEE 0.005 and MAX_HISTORY 50 are #define constants at the top of aethervault.h

- Price display always uses %.2f; percentage changes use %+.2f%% (note: double %% for literal %)

- Every scanf() call in the trading menu must be followed by a loop clearing the input buffer with getchar()

- math.h functions (sqrt, pow, fabs) are used directly in the Risk Engine volatility calculations

Session Calendar — 19 Jun – 21 Jun

| Session | Date | Focus | Hours |
| --- | --- | --- | --- |
| S1 | Fri 19 Jun | Watch timestamps 0:00–0:54: intro, setup, data types, format specifiers, constants, operators, scanf(). Type every example by hand. No copy-paste. | 4 h |
| S2 | Sat 20 Jun | Watch 0:55–1:01 (math.h). Gap-filler videos: printf column alignment, format specifiers, scanf buffer clearing, #define vs const. Experiment in test.c. | 4 h |
| S3 | Sun 21 Jun | Task 1 — Stock Price Table Printer. Task 2 — Safe Input Validator. Task 3 — Math.h Exploration. Verify output. Review ALL compile warnings. | 4 h |
| REST | Mon 22 Jun | Mandatory rest day — brain consolidates knowledge during sleep. No coding. | — |

Mandatory Practice Tasks

Task 1: Stock Price Table Printer Define 5 hardcoded stocks as separate variables (no arrays yet). Print as a formatted table with columns: Symbol (left-aligned, 8 chars), Price (right-aligned, 10.2f), Change% (right-aligned, +7.2f%%). Add a dashed divider line. Expected output must look like a real console app, not raw numbers.

Task 2: Safe Input Validator Ask the user to enter a cash balance (double). Use a do-while loop to reject any value ≤ 0 with a clear error message. After valid entry, print: Balance set to $X,XXX.XX using %.2f. Then ask for a transaction amount and check it does not exceed the balance.

Task 3: Math.h Exploration Take a stock base volatility (double, e.g. 0.02) and use pow(), sqrt(), and fabs() to compute: daily variance = vol^2, daily std dev = sqrt(variance), absolute daily move = fabs(price*vol). Print all three with labels and 6 decimal places. Link each result to how it appears in the AetherVault risk engine.

| PHASE 2 — Control Flow, Loops, Functions | 22 Jun – 24 Jun 12 Hours | 3 sessions × 4 hrs |
| --- | --- | --- |

Bro Code Timestamps to Watch

- 1:02:00 – 1:13:59   if / else if / else — conditional branching

- 1:14:00 – 1:22:59   switch statements — multi-branch menus

- 1:23:00 – 1:29:59   while loops — condition-checked entry

- 1:30:00 – 1:36:59   do-while loops — guaranteed-first-execution loops

- 1:37:00 – 1:47:59   for loops — counter-controlled iteration

- 1:48:00 – 1:57:59   Functions: declaration, definition, parameters, return values

- 1:58:00 – 2:04:59   Function prototypes (forward declarations)

- 2:05:00 – 2:14:59   Variable scope: local vs. global

Gap Analysis — What Bro Code Does NOT Cover

- Passing arrays or pointers to functions — critical mental model to build NOW, before Phase 4

- Multi-file function organisation — you need prototypes before you can split files

- switch fallthrough behaviour and why you ALWAYS need break — not emphasised by Bro Code

- Returning multiple values via output parameters (pointers) — not covered but needed in Phase 4

- Infinite loop pattern: while(1) { ... } used for the main game loop — not shown as a design pattern

- Nested loops for 2D data structures (price history across multiple stocks) — barely touched

- Early exit patterns: break vs. continue vs. return — not compared side-by-side

Gap-Filler Resources

- YouTube: “C switch statement menu system tutorial”

- YouTube: “C do while input validation loop tutorial”

- YouTube: “C function prototypes explained beginners”

- YouTube: “C while 1 game loop pattern C programming”

- Jacob Sorber: “Writing Clean C” — excellent for function design habits (search exact title)

- YouTube: “C break continue return difference explained”

Project Relevance — AetherVault Trader Connection

- The ENTIRE AetherVault program is structured as: while(1) { show_main_menu(); switch(get_input()) {…} }

- Every feature is a function: buy_stock(), sell_stock(), show_portfolio(), run_market_tick()

- do-while forces re-entry on an invalid symbol until a valid one is provided

- Function prototypes in aethervault.h allow the project to be split into 8 separate .c files

- Nested for loops iterate price history across every stock and every recorded tick

Session Calendar — 22 Jun – 24 Jun

| Session | Date | Focus | Hours |
| --- | --- | --- | --- |
| S1 | Mon 22 Jun | Watch timestamps 1:02–1:47: if/else, switch, while, do-while, for loops. Build a small menu in test.c. Gap-filler: switch menu system video. | 4 h |
| S2 | Tue 23 Jun | Watch 1:48–2:14: functions, prototypes, scope. Gap-filler: while(1) game loop pattern. Jacob Sorber Writing Clean C video. Practise utility functions. | 4 h |
| S3 | Wed 24 Jun | Task 1 — Full Console Menu System. Task 2 — Market Tick Simulator. Task 3 — Input Validation Function Library. Keep these in utils.c. | 4 h |
| REST | Thu 25 Jun | Mandatory rest day — brain consolidates knowledge during sleep. No coding. | — |

Mandatory Practice Tasks

Task 1: Full Console Menu System Build a menu: 1) Deposit Cash 2) Withdraw Cash 3) Check Balance 4) Quit. Use while(1) + switch. Each option calls a separate function. Deposit/withdraw use do-while to reject invalid amounts. Balance can never go negative. On quit, print the final balance and exit cleanly.

Task 2: Market Tick Simulator (no structs yet) Write simulate_tick(double price, double volatility) that returns a slightly randomised new price using rand(). Call it 10 times in a for loop and print each new price. Seed with srand(time(NULL)). Link the output visually to how price history will look in AetherVault.

Task 3: Input Validation Function Library Write three utility functions: get_positive_double(prompt), get_positive_int(prompt), and get_string(prompt, buf, maxlen). Each must loop until valid input. These are real utility functions you will reuse verbatim in AetherVault — keep them in utils.c.

| PHASE 3 — Arrays, Strings, String Functions | 25 Jun – 27 Jun 12 Hours | 3 sessions × 4 hrs |
| --- | --- | --- |

Bro Code Timestamps to Watch

- 2:15:00 – 2:27:59   Arrays: declaration, indexing, iteration

- 2:28:00 – 2:37:59   2D arrays — price history grids

- 2:38:00 – 2:49:59   Strings as char arrays, null terminator

- 2:50:00 – 2:57:59   String functions: strlen, strcpy, strcat, strcmp

- 2:58:00 – 3:09:59   More string.h: strupr, strlwr overview

Gap Analysis — What Bro Code Does NOT Cover

- strncpy (safe copy) — Bro Code uses strcpy which is unsafe for fixed buffers; strncpy is mandatory in AetherVault

- strstr() for substring search — needed for the search-by-symbol feature in the main menu

- sprintf() and snprintf() for building formatted strings — absent but critical for table row rendering

- The null-terminator bug: forgetting to terminate after strncpy — causes silent memory corruption

- Relationship between arrays and pointers — hinted at but not explained clearly; essential bridge to Phase 4

- Fixed-array limitations: why you cannot size an array by a runtime user input — directly motivates malloc in Phase 6

- toupper()/tolower() for normalising ticker symbol input — not mentioned by Bro Code

Gap-Filler Resources

- YouTube: “C strings strncpy safe string copy tutorial”

- YouTube: “C strstr string search function tutorial”

- YouTube: “C sprintf snprintf string formatting”

- YouTube: “C arrays and pointers relationship explained”

- YouTube: “C null terminator string bugs common mistakes”

- CS50 Week 2 — excellent treatment of strings as char arrays (cs50.harvard.edu)

- YouTube: “C toupper tolower ctype.h tutorial”

Project Relevance — AetherVault Trader Connection

- Every ticker symbol is stored as char symbol[8] — strncpy copies it safely, strcmp compares for exact match search

- Stock search feature loops through the market array comparing symbols with strcmp()

- snprintf builds formatted table rows into a buffer before printing — used in the portfolio display function

- Transaction log stores a type string of BUY or SELL — assigned and compared with string functions

- Understanding array-pointer duality NOW makes Phase 4 pointers far easier to grasp

- toupper() in a loop normalises user input like ‘nvda’ to ‘NVDA’ before strcmp comparison

Session Calendar — 25 Jun – 27 Jun

| Session | Date | Focus | Hours |
| --- | --- | --- | --- |
| S1 | Thu 26 Jun | Watch 2:15–2:37: arrays (1D and 2D). Watch 2:38–3:09: strings, null terminator, string functions. Do NOT use strcpy in your own code — use strncpy. | 4 h |
| S2 | Fri 27 Jun | Gap-fillers: strncpy / strstr / snprintf videos. Rewrite all test.c string code using strncpy. Gap-fillers: arrays-and-pointers relationship, toupper/tolower. CS50 Week 2 strings section. | 4 h |
| S3 | Sat 28 Jun | Task 1 — Hardcoded Stock Registry with Search. Task 2 — Safe String Input Function. Task 3 — snprintf Table Row Builder. This is literally the AetherVault portfolio printer — do it well. | 4 h |
| REST | Sun 29 Jun | Mandatory rest day — brain consolidates knowledge during sleep. No coding. | — |

Mandatory Practice Tasks

Task 1: Hardcoded Stock Registry with Search Create an array of 5 structs (preview structs here), each with a symbol string and a price. Fill with hardcoded data. Write search_by_symbol() that takes the array, its size, and a query string; uses strcmp() in a for loop; returns the index or -1. Print found/not-found with full details.

Task 2: Safe String Input Function Write read_symbol(buf, max) that uses fgets(), strips the trailing newline, converts to uppercase using toupper() in a loop, and validates: length > 0 and ≤ 6 characters. This is production code you will use verbatim in AetherVault buy/sell menus.

Task 3: snprintf Table Row Builder Write build_row(out, outlen, sym, qty, price, value) using snprintf with aligned formatting. Print 5 rows. Add a header and a dashed separator. This IS the portfolio table printer — the format string goes directly into AetherVault.

| PHASE 4 — POINTERS: The Most Critical Phase | 28 Jun – 30 Jun 15 Hours | 3 sessions × 5 hrs |
| --- | --- | --- |

CAUTION: DO NOT RUSH THIS PHASE. Pointers are the backbone of every advanced feature in AetherVault Trader. If you do not understand them deeply, you cannot build the dynamic stock list, the transaction log, the portfolio functions, or the save system correctly. Take every extra hour this needs. Draw memory diagrams on paper for EVERY exercise. If you cannot draw it on paper with boxes and arrows, you do not understand it yet.

Bro Code Timestamps to Watch

- 3:10:00 – 3:21:59   Pointers: address-of (&), dereference (*), pointer variables

- 3:22:00 – 3:29:59   Passing by reference with pointers (vs. pass by value)

- 3:30:00 – 3:37:59   Pointer arithmetic — advancing through arrays

- 3:38:00 – 3:44:59   Arrays and pointers: why arr equals the address of arr[0]

- 3:45:00 – 3:54:59   Strings and char pointers

Gap Analysis — What Bro Code Does NOT Cover

- Pointers to structs and the -> operator — barely shown, absolutely essential for all AetherVault functions

- Double pointers (**) — required when a function must change a pointer itself (growing the stock array)

- NULL pointer: what it is, when malloc returns it, and why you MUST check it before every dereference

- Dangling pointers: what happens when you free() memory and keep using the old pointer address

- Pointer to const vs. const pointer — used for read-only function parameters in AetherVault

- Common pointer bugs: off-by-one, uninitialized pointer, forgetting to dereference

Gap-Filler Resources

- YouTube: “CS50 2023 Week 4: Memory” — THE best pointer lecture in existence, completely free

- YouTube: “Jacob Sorber pointers tutorial C”

- YouTube: “C double pointer explained simply beginners”

- YouTube: “C pointer to struct arrow operator tutorial”

- YouTube: “C NULL pointer check malloc best practice”

- YouTube: “C dangling pointer memory bug explained”

- YouTube: “CodeVault C pointers tutorial”

Project Relevance — AetherVault Trader Connection

- The dynamic market array is held entirely through a Stock pointer that starts as NULL

- The single user portfolio is accessed throughout the program via a Portfolio pointer

- The -> operator is how every function reaches into a struct through its pointer to read or modify fields

- buy_stock() takes a pointer to the portfolio and a pointer to the stock so it can modify cash directly

- Growing the market array requires a double pointer so realloc's result can be written back to the caller

Reference Code Pattern

// These exact patterns appear throughout AetherVault: Stock *market = NULL; // pointer to dynamic market array Portfolio *p = &user_portfolio; // pointer to the one portfolio p->cash -= cost; // -> operator // Function that MODIFIES the portfolio (pass by pointer): void buy_stock(Portfolio *p, const Stock *s, int qty) { p->cash -= qty * s->price * (1 + TRANSACTION_FEE); add_holding(p, s->symbol, qty, s->price); } // Growing the market array (double pointer pattern): void add_market_stock(Stock **market, int *count, Stock new_stock) { Stock *tmp = realloc(*market, (*count + 1) * sizeof(Stock)); if (!tmp) { return; } *market = tmp; (*market)[(*count)++] = new_stock; }

Session Calendar — 28 Jun – 30 Jun

| Session | Date | Focus | Hours |
| --- | --- | --- | --- |
| S1 | Sun 28 Jun | Watch 3:10–3:54: pointers, address-of, dereference, pass-by-reference, pointer arithmetic, arrays+pointers, char pointers. Jacob Sorber pointers video. Draw memory diagrams for every example. | 5 h |
| S2 | Mon 29 Jun | CS50 Week 4 Memory lecture — full (~2 hours). This is the single most valuable session in the roadmap. Gap-fillers: double pointer, -> operator, NULL pointer checks, dangling pointers. Draw diagrams. | 5 h |
| S3 | Tue 30 Jun | Task 1 — Swap and Double via Pointers (draw full stack diagram first). Task 2 — Struct Via Pointer. Task 3 — Growing Array via Double Pointer. One diagram per task. No diagram = not done. | 5 h |
| REST | Wed 1 Jul | Mandatory rest day — brain consolidates knowledge during sleep. No coding. | — |

Mandatory Practice Tasks

Task 1: Swap and Double via Pointers Write swap(int *a, int *b) and double_it(int *n). Then write update_price(double *price, double change_pct) that modifies a price in place. Print before and after for each. REQUIRED: draw the stack diagram showing what happens to *price when update_price() executes. No diagram = not done.

Task 2: Struct Via Pointer Define a simple Account struct with a balance and an id. Write deposit(Account *acc, double amount) and withdraw(Account *acc, double amount) — withdraw must check for sufficient funds and return 0 on failure. Access all members with ->. Draw the memory layout.

Task 3: Growing Array via Double Pointer Write append_int(int **arr, int *count, int value). It must: realloc *arr to count+1 integers, NULL-check the result, store the value, increment *count. In main, start with arr=NULL and count=0, call append_int 5 times, print all, then free(arr). This is the core pattern behind add_transaction().

| PHASE 5 — Structures, Typedef, Nested Structs | 1 Jul – 3 Jul 12 Hours | 3 sessions × 4 hrs |
| --- | --- | --- |

Bro Code Timestamps to Watch

- 3:55:00 – 4:04:59   Structs: declaration, member access, initialisation

- 4:05:00 – 4:11:59   Structs as function parameters (pass by value vs. by pointer)

- 4:12:00 – 4:24:59   Typedef — creating clean type aliases for structs

Gap Analysis — What Bro Code Does NOT Cover

- Nested structs: a Portfolio containing an array of Holdings — Bro Code never shows this pattern

- Arrays of structs — shown briefly but never iterated with real functions

- Structs + pointers together (the -> operator in multi-function programs) — minimal example

- Designing struct layout before coding: what fields belong in which struct — not taught as discipline

- Struct padding and sizeof() — critical for binary file I/O in Phase 7 (misaligned reads = corrupt data)

- Forward declarations of structs — needed when two structs reference each other in aethervault.h

Gap-Filler Resources

- YouTube: “C struct array of structs tutorial”

- YouTube: “C nested structs example tutorial”

- YouTube: “C typedef struct best practices”

- Jacob Sorber: “Structures in C” and “Linked Lists in C” (exact titles — search YouTube)

- YouTube: “C sizeof struct memory layout padding”

Project Relevance — AetherVault Trader Connection

- All 4 AetherVault structs are defined in aethervault.h: Stock, Holding, Transaction, Portfolio

- Portfolio contains a dynamic array of Holdings and a dynamic array of Transactions

- All trading functions take a Portfolio pointer and modify fields with the -> operator

- sizeof(Stock) and sizeof(Transaction) must be exact for correct binary save/load in Phase 7

- Forward declarations let the file-I/O module use Portfolio without circular includes

Reference Code Pattern

// -- aethervault.h -- typedef struct { char symbol[8]; // e.g. NVDA char name[32]; // e.g. NVIDIA Corp double price; // current price double volatility; // e.g. 0.025 = 2.5% daily vol double drift; // mean return per tick double history[50]; // last 50 prices for ASCII chart int hist_count; } Stock; typedef struct { char symbol[8]; int quantity; double avg_buy_price; double realized_pnl; } Holding; typedef struct { char type[8]; // BUY or SELL char symbol[8]; int quantity; double price; double fee; long timestamp; } Transaction; typedef struct { double cash; Holding *holdings; // dynamic array int holding_count; Transaction *history; // dynamic array int history_count; } Portfolio;

Session Calendar — 1 Jul – 3 Jul

| Session | Date | Focus | Hours |
| --- | --- | --- | --- |
| S1 | Thu 2 Jul | Watch 3:55–4:24: structs, function parameters, typedef. Build a Stock struct in test.c. Gap-fillers: array of structs, nested structs videos. Build Holding and Transaction. | 4 h |
| S2 | Fri 3 Jul | Jacob Sorber Structures in C video. Add -> pointer access to all struct practice code. sizeof() and struct padding gap-filler. Verify sizeof(Stock), sizeof(Transaction). | 4 h |
| S3 | Sat 4 Jul | Task 1 — Student Record System. Task 2 — Nested Struct Address in Person. Task 3 — Design Your AetherVault Structs on paper. This is your project blueprint — be thorough. | 4 h |
| REST | Sun 5 Jul | Mandatory rest day — brain consolidates knowledge during sleep. No coding. | — |

Mandatory Practice Tasks

Task 1: Student Record System Define a Student struct with name, age, and GPA. Create an array of 5. Write print_student() using ->. Write find_by_name() returning a pointer. Write highest_gpa() returning a pointer. Print results.

Task 2: Nested Struct: Address in Person Define an Address struct (city, country) and a Person struct that contains a name, age, and a nested Address. Create a Person, fill all fields, access via pointer with ->. Modify the city through the pointer. Draw the nested memory layout.

Task 3: Design Your AetherVault Structs On paper or in a text file, write out all 4 AetherVault structs (Stock, Holding, Transaction, Portfolio) with every field, its type, and a one-line comment explaining WHY each field exists. Draw a diagram showing which struct contains pointers to which. This is your project blueprint.

| PHASE 6 — Dynamic Memory: malloc, calloc, realloc, free | 4 Jul – 6 Jul 15 Hours | 3 sessions × 5 hrs |
| --- | --- | --- |

CAUTION: This phase is the number one source of project-killing bugs for beginners. Memory leaks, double-frees, and use-after-free crashes are all born here. Bro Code coverage is surface-level. Use every gap-filler listed below, and run Valgrind on every practice program. Rule: zero Valgrind leaks is the ONLY acceptable result. There is no “mostly clean.”

Bro Code Timestamps to Watch

- 4:25:00 – 4:32:59   malloc() and free() — heap allocation basics

- 4:33:00 – 4:37:59   calloc() — zeroed allocation for clean initialisation

- 4:38:00 – 4:43:59   realloc() — resize an existing allocation

- 4:44:00 – 4:52:59   Memory leaks overview

Gap Analysis — What Bro Code Does NOT Cover

- Growing a dynamic struct array with realloc in a loop — the primary pattern, barely touched

- Always storing the realloc result in a TEMP pointer first — never reassign the original pointer directly

- Freeing nested dynamic structures in the correct order (free holdings before freeing the portfolio)

- calloc vs malloc: when zero-initialisation matters (zeroing a new Holding avoids garbage field reads)

- Valgrind usage with full leak-check flags — not mentioned at all by Bro Code

- The NULL check pattern after EVERY single malloc/realloc — non-negotiable in production code

- Memory alignment: why sizeof(Holding) times n gives the correct byte count for realloc

Gap-Filler Resources

- YouTube: “C malloc calloc realloc free complete tutorial”

- YouTube: “C dynamic array realloc grow array tutorial”

- YouTube: “C dynamic array of structs malloc example”

- Jacob Sorber: “Dynamic Memory in C” (search exact title on YouTube)

- YouTube: “Valgrind memory leak detection C tutorial”

- YouTube: “C realloc safe pattern temp pointer”

Project Relevance — AetherVault Trader Connection

- add_holding() grows the holdings array with the safe realloc-into-temp-pointer pattern

- add_transaction() uses the same safe realloc pattern for the transaction history array

- free_portfolio() must free holdings first, then history, and NULL both pointers

- Portfolio starts with both array pointers NULL and both counts at zero

- Valgrind must show zero leaks before you are cleared to start the build phase

Reference Code Pattern

// -- add_holding(): grow holdings array safely -- void add_holding(Portfolio *p, const char *sym, int qty, double price) { Holding *tmp = realloc(p->holdings, (p->holding_count + 1) * sizeof(Holding)); if (!tmp) { fprintf(stderr, "Out of memory"); exit(1); } p->holdings = tmp; Holding *h = &p->holdings[p->holding_count++]; strncpy(h->symbol, sym, sizeof(h->symbol) - 1); h->symbol[sizeof(h->symbol) - 1] = 0; h->quantity = qty; h->avg_buy_price = price; h->realized_pnl = 0.0; } // -- free_portfolio(): always free in correct order -- void free_portfolio(Portfolio *p) { free(p->holdings); p->holdings = NULL; free(p->history); p->history = NULL; }

Session Calendar — 4 Jul – 6 Jul

| Session | Date | Focus | Hours |
| --- | --- | --- | --- |
| S1 | Sat 4 Jul | Watch 4:25–4:52: malloc, calloc, realloc, free. Jacob Sorber Dynamic Memory video. Gap-filler: realloc safe-pattern (temp pointer). Practise in test.c: grow an int array safely 10 times. | 5 h |
| S2 | Sun 5 Jul | Valgrind installation and tutorial video. Run Valgrind on ALL previous test.c programs. Fix ALL leaks. Gap-filler: dynamic array of structs, NULL check pattern. Build add_holding() in isolation. | 5 h |
| S3 | Mon 6 Jul | Task 1 — Dynamic Integer List with Valgrind. Task 2 — Dynamic Struct Array with remove_item(). Task 3 — Nested Dynamic Structures with full cleanup. Run Valgrind: zero leaks required. | 5 h |
| REST | Tue 7 Jul | Mandatory rest day — brain consolidates knowledge during sleep. No coding. | — |

Mandatory Practice Tasks

Task 1: Dynamic Integer List Start with a NULL int pointer and a count of 0. Write append(int **list, int *count, int val) using the SAFE realloc pattern (temp pointer, NULL check). Call it 8 times. Print all. Free the list. Run with Valgrind — must show zero errors, zero leaks. Fix anything Valgrind finds before moving on.

Task 2: Dynamic Struct Array with Removal Define a simple Item struct with a name and a price. Write add_item() with safe realloc. Add 5 items. Write remove_item() that shifts remaining items left and reallocs down. Print after each removal. Run Valgrind on the full program.

Task 3: Nested Dynamic Structures with Full Cleanup Define a simplified Portfolio with cash, a dynamic Holding array, and a dynamic Transaction array. Write add_holding() and add_transaction() exactly as shown above. Add 3 holdings and 4 transactions. Write free_portfolio() that frees both arrays and NULLs the pointers. Valgrind: zero leaks required.

| PHASE 7 — File I/O, Math, Random Walk, ANSI, time.h | 7 Jul – 9 Jul 12 Hours | 3 sessions × 4 hrs |
| --- | --- | --- |

Bro Code Timestamps to Watch

- 5:00:00 – 5:11:59   File I/O: fopen, fclose, fprintf, fscanf

- 5:12:00 – 5:19:59   Reading and writing text files

- 5:20:00 – 5:27:59   fwrite and fread — binary file I/O

- 5:28:00 – 5:39:59   Checking if a file exists, error handling with fopen

- 0:55:00 – 1:01:59   Revisit: math.h — exp(), log(), sqrt() for price simulation

- 0:43:00 – 0:54:59   Revisit: rand(), srand(), RAND_MAX — proper seeding

Gap Analysis — What Bro Code Does NOT Cover

- Binary fwrite/fread with structs — Bro Code is very shallow; this is the cleanest AetherVault save approach

- Saving dynamic arrays: write the count first, then the full array

- ANSI escape codes for terminal colour — completely absent from Bro Code course

- time.h timestamping for transaction records — not covered

- The Box-Muller transform for Gaussian random numbers — needed for realistic price simulation

- exp() and log() for a geometric random walk on price — not covered

- perror() for file operation error messages — essential for debugging save/load failures

Gap-Filler Resources

- YouTube: “C file I/O fwrite fread binary structs tutorial”

- YouTube: “C save load struct array binary file”

- YouTube: “ANSI escape codes terminal colors C tutorial”

- YouTube: “C time.h timestamp strftime tutorial”

- YouTube: “C Gaussian random number Box-Muller transform”

- Jacob Sorber: “Reading and Writing Files in C” — covers binary I/O deeply (search exact title)

Project Relevance — AetherVault Trader Connection

- save_portfolio() writes the cash value, then the holding count, then the full holdings array

- ANSI colour macros mark gains green and losses red directly in the terminal output

- gaussian() implements the Box-Muller transform to produce normally-distributed random shocks

- next_price() applies a geometric random walk using exp() with drift and the Gaussian shock

Reference Code Pattern

// -- Binary save: write count then array -- void save_portfolio(const Portfolio *p, const char *filename) { FILE *f = fopen(filename, "wb"); if (!f) { perror("Save failed"); return; } fwrite(&p->cash, sizeof(double), 1, f); fwrite(&p->holding_count, sizeof(int), 1, f); fwrite(p->holdings, sizeof(Holding), p->holding_count, f); fclose(f); } // -- ANSI colour macros -- #define CLR_GREEN "\033[0;32m" #define CLR_RED "\033[0;31m" #define CLR_RESET "\033[0m" // -- Price simulation: geometric random walk -- double gaussian(void) { double u1 = (rand() + 1.0) / (RAND_MAX + 2.0); double u2 = (rand() + 1.0) / (RAND_MAX + 2.0); return sqrt(-2.0 * log(u1)) * cos(2.0 * M_PI * u2); } double next_price(double old, double drift, double vol) { return old * exp(drift + vol * gaussian()); }

Session Calendar — 7 Jul – 9 Jul

| Session | Date | Focus | Hours |
| --- | --- | --- | --- |
| S1 | Wed 8 Jul | Watch 5:00–5:39: fopen/fclose, text and binary file I/O, error handling. Jacob Sorber Reading and Writing Files in C. Gap-filler: binary save/load of struct arrays. Implement save_portfolio(). | 4 h |
| S2 | Thu 9 Jul | ANSI escape codes gap-filler. Implement all CLR_ macros. Build a colour-coded test table. time.h gap-filler. Re-watch 0:43–1:01 (rand, math.h). Implement gaussian() and next_price(). | 4 h |
| S3 | Fri 10 Jul | Task 1 — Binary Save/Load. Task 2 — ANSI Colour Table. Task 3 — Price History Simulator with ASCII Chart. By end of this session: LEARNING PHASE IS COMPLETE. | 4 h |

Mandatory Practice Tasks

Task 1: Binary Save/Load of Dynamic Struct Array Using the Portfolio from Phase 6 Task 3: write save_portfolio() and load_portfolio() using fwrite/fread exactly as shown above. Save 3 holdings and 4 transactions. Quit the program. Reload and verify EVERY field matches exactly. Any mismatch means a binary layout bug.

Task 2: ANSI Colour Table Print a table of 5 stocks with a P&L column. If P&L > 0: entire row in green. If P&L < 0: red. If P&L == 0: yellow. Add a blue header row. Add a reset escape at the end of every row. Test in a real terminal — not all IDEs support ANSI codes.

Task 3: Price History Simulator with ASCII Chart Implement gaussian() and next_price(). Simulate 50 ticks for one stock (start $100, small drift, vol=0.02). Store in a history array. Print an ASCII line chart: find min/max, scale to 10 rows of height, print row by row. This IS the AetherVault price history chart feature.

# D.  Build Phase — 10 Jul to 15 Jul 2026

| BUILD PHASE — Full Project Assembly | 10 Jul – 15 Jul 36 Hours | 6 sessions × 6 hrs |
| --- | --- | --- |

All learning is complete. Every concept needed for AetherVault Trader has now been covered, practised, and connected directly to a real project feature. This phase is pure assembly: no new C concepts, only applying what you already know across 8 source files. Build incrementally — compile and test after every single function, never write more than 30-40 lines before recompiling.

## Source File Structure

| File | Responsibility |
| --- | --- |
| aethervault.h | All struct definitions (Stock, Holding, Transaction, Portfolio), #define constants, and function prototypes for every module. |
| main.c | Entry point. Initialises the market and portfolio, runs the while(1) main menu loop, calls save on exit. |
| market.c | Market initialisation with 10+ hardcoded stocks, the random-walk tick engine (gaussian + next_price), and price history tracking. |
| trading.c | buy_stock() and sell_stock() with full validation, the 0.5% transaction fee, and updates to holdings and transaction history. |
| portfolio.c | Portfolio display: formatted holdings table with live P&L, cash balance, and total portfolio value, all colour-coded with ANSI codes. |
| risk.c | Volatility, beta-style risk score, and a diversification score across holdings, plus the ASCII price chart renderer. |
| fileio.c | save_portfolio() and load_portfolio() using binary fwrite/fread, with full error handling via perror(). |
| utils.c | Safe input functions (get_positive_double, get_positive_int, read_symbol), string helpers, and the search-by-symbol feature. |

## Day-by-Day Build Milestones

| Day | Focus | Deliverable | Hours |
| --- | --- | --- | --- |
| Day 22 — Fri 10 Jul | Core data and market engine | aethervault.h finalised with all 4 structs. market.c complete: 10+ stocks initialised, random-walk tick engine working, prices update correctly on each tick. | 6 h |
| Day 23 — Sat 11 Jul | Trading and portfolio core | trading.c complete: buy_stock() and sell_stock() with fee calculation and full validation. portfolio.c: dynamic holdings array updates correctly on every trade. | 6 h |
| Day 24 — Sun 12 Jul | Display, persistence, risk engine | Portfolio table renders with ANSI colours and correct P&L. fileio.c: save/load tested with a full round-trip (save, quit, reload, verify). risk.c: volatility and diversification scores computed. | 6 h |
| Day 25 — Mon 13 Jul | UI polish and extra features | Main menu fully wired with every option working end-to-end. Stock search, transaction filtering, and the ASCII risk chart implemented. Error messages reviewed for clarity. | 6 h |
| Day 26 — Tue 14 Jul | Integration testing and bug fixing | Full run-through of every menu path. Valgrind run on the complete program — zero leaks required. Edge cases tested: zero balance, max holdings, invalid symbols, corrupted save file. | 6 h |
| Day 27 — Wed 15 Jul | Final delivery day | Final compile with zero warnings (use -Wall -Wextra). Full feature checklist verified against Section A requirements. AetherVault Trader is FULLY WORKING and complete. | 6 h |

## Final Delivery Checklist — 15 July 2026

- 10+ stocks simulated with a random walk that includes drift - Price history of 50 ticks stored and rendered as an ASCII chart - Buy and sell functions with 0.5% transaction fee and full input validation - Portfolio table showing symbol, quantity, average price, and live P&L - All core data stored in dynamically allocated memory — no fixed-size arrays for stocks or transactions - Binary save and load of the full portfolio and transaction history - Risk engine: volatility, a beta-style score, and a diversification score - ANSI colour-coded terminal output throughout - Stock search by symbol and transaction history filtering - Zero memory leaks confirmed with Valgrind - Zero compiler warnings with -Wall -Wextra - Clean exit that saves state automatically

Deadline: 15 July 2026 — AetherVault Trader must be fully working, end to end.